# Creative Brief — Brand Refresh

Project: Sample Client — Brand Refresh, Phase 1.

Background: Sample Client is a 12-year-old direct-to-consumer brand seeking to modernize its visual identity ahead of a 2026 product launch. The current logo and palette were designed in 2014 and feel dated relative to category competitors.

Objectives: Establish a refreshed identity system (logo, type, color, voice) that signals innovation while preserving brand equity. Deliverables include the primary logo, secondary marks, type system, color palette, and a one-page brand voice guide.

Audience: Primary — existing customers (35-55, professional, brand-loyal). Secondary — net-new prospects (28-45, design-aware, comparison shoppers).

Tone and feel: Confident, modern, restrained. Not playful. Not corporate. Reference brands include those in the premium-mid market with strong typographic systems.

Constraints: Must work in single color (mono) at 16px favicon size. Must remain legible on dark and light backgrounds. Final files in SVG, PNG, and brand book in PDF.

Timeline: Discovery (2 weeks). Concepts (3 weeks, two rounds). Refinement and final delivery (3 weeks). Total 8 weeks from kickoff.

Budget: $25,000 fixed-fee, payable 30/40/30 against milestones.